## Sheet1
Project: e-angona | Task Type | Task | Details | Estimation(mn) | Status
| Project | Thinking |  | 2 | Done
| Environment | MS SQL Server |  | 60 | Done
|  | Python |  | 5 | Done
|  | Django/Flask/Desk |  | 30 | Done
| Backend Database | Database e-angona |  | 5 | Done
|  | Table church_group | id, name | 5 | Done
|  | Table church | id, name, group_id | 5 | Done
|  | Table believer | id, name, firstName, pwd, church_id | 5 | Done
|  | Table loan | id, believer_id, request_date, delivery_date, repay_date,amount | 5 | Done
|  | Table donation | id, church_id, amount, date, Sunday_id | 5 | Done
|  | Table event | id, believer_id, event_type, date
|  | Table event_type | id, name
| Backend Models | Believer | id, name, firstName, church_id | 5 | Not Started
|  | ChurchGroup | id, name | 5 | Done
|  | Church | id, name, firstName, group_id | 5 | Not Started
|  |  | getFund(year, Sunday_id) -> Donation[] | 15 | Not Started
|  |  | getDonation(year) -> Donation[] | 15 | Not Started
|  |  | getLatestLoan() -> Loan | 15 | Not Started
|  |  | calculatePercentage(actualYear, pastYear)-> double | 15 | Not Started
|  | Loan | id, believer_id, request_date, delivery_date, repay_date, amount | 5 | Not Started
|  |  | calculateSundayCount()->int | 15 | Not Started
|  |  | calculateDeliveryDate()->Loan | 30 | Not Started
|  | Donation | id, church_id, amount, date, Sunday_id | 5 | Not Started
|  | Utilities | sum(Object[], attrName)->double | 15 | Not Started
|  | Database | getConnection() | 15 | Not Started
|  | DbObject | insert | 30 | Not Started
|  |  | update | 30 | Not Started
|  |  | delete | 30 | Not Started
|  |  | read | 30 | Not Started
| Front end templates | Donation form | input:date, amount, submit-btn | 15 | Not Started
|  | Loan request form | input:number, date | 30 | Not Started
|  | Login/Signup form | input:name, firstName, password, church | 30 | Not Started
|  |  | Total in mn | 482
|  |  | Total in h | 8.0333